## 0 · Read me
GWEA 2.0 · EXAMPLE OUTPUTS
GWEA 2.0 — what each stage produces
A gallery of worked example outputs · Department of Human Settlements (Vote 33) · Cycle C2 · 2026/27 baseline
Tab | What output it shows
1 · Catalogue (P1) | Phase 1 output — the categorised architecture catalogue: 15 elements in five layers, populated.
2 · Assessment (P2) | Phase 2 output — maturity scores per element, zones, a spider chart and a chain (root-cause) analysis.
3 · Roadmap (P3) | Phase 3 output — prioritised focus areas (by weighted gap) and a three-horizon transition roadmap.
4 · Remedial (P4) | Phase 4 output — the remedial-action portfolio / delivery dashboard with RAG status.
5 · Governance (P5) | Phase 5 output — ARB register, principle adherence and transformation impact.
EE · Catalogue | Enabling Environment cataloguing — the register of what exists per readiness dimension, in five clusters.
EE · Readiness | Enabling Environment assessment — 11-dimension readiness, a spider chart and the hard-gate verdict.
The enabling environment is catalogued and assessed exactly like the architecture: EE · Catalogue is its Phase-1 register (what exists per dimension); EE · Readiness is its Phase-2 assessment. Every figure is illustrative training data built from the DHS PEAR workbook. Maturity is scored 0–5 (EE readiness 0–4) and classified into four zones under worst-dimension-wins.

## 1 · Catalogue (P1)
PHASE 1 OUTPUT · ARCHITECTURE CATALOGUE
Phase 1 — Architecture Catalogue
The categorised register of what the department is and has — 15 elements across five layers, populated with real items.
Grouping | Element / dimension | Catalogue items (illustrative) | Count
Motivation | 1. Outcome | Sustainable human settlements & improved household quality of life · Fully subsidised houses delivered · Security of tenure — title deeds registered · Informal settlements upgraded · Serviced sites delivered · Affordable rental & social housing delivered · Affordable housing finance (First Home Finance) | 7
| 2. Client | Qualifying low-income households (subsidy applicants) · Informal settlement households · First-time home buyers (gap market) · Social / rental housing tenants · Provincial departments (delivery agents) · Metropolitan municipalities (delivery agents) · Home builders / property practitioners (regulated) · Community scheme owners and occupiers · Emergency housing beneficiaries (disaster-affected) · Digitally excluded applicants (rural, elderly) | 10
| 3. Value Proposition | A subsidised home for qualifying households · Secure, registered title to your home · Basic services and tenure in upgraded settlements · Access to affordable housing finance · Published service standards (Batho Pele charter) | 5
Strategy | 4. Capability | Administration & corporate governance · Integrated human settlements planning & development · Grant management (HSDG / USDG) · Informal settlements upgrading · Rental and social housing · Affordable housing finance facilitation · Public entity oversight · Monitoring & evaluation · Beneficiary management & subsidy administration · ICT and digital services | 10
| 5. Location | National (DHS head office) · Eastern Cape · Free State · Gauteng · KwaZulu-Natal · Limpopo · Mpumalanga · North West · Northern Cape · Western Cape | 10
Business | 6. Product | Housing subsidy / BNG house · Title deed · Serviced site · Rental / social housing unit · First Home Finance subsidy | 5
| 7. Service | Subsidy application & approval · Beneficiary registration · Title-deed issuance · Informal-settlement upgrading · Housing consumer complaints | 5
| 8. Process | Subsidy adjudication process · Project approval & disbursement · Beneficiary verification · Title transfer & registration | 4
IS Solution | 9. Application | Housing Subsidy System (HSS) · National Housing Needs Register · Grant management spreadsheets · Provincial project registers | 4
| 10. Data Access | HSS ↔ Deeds Office · HSS ↔ provincial systems · Needs Register ↔ municipalities · Beneficiary ↔ Home Affairs (ID verification) | 4
| 11. Master Data | Beneficiary master · Project master · Property / erf master · Provincial delivery-agent master | 4
| 12. Transaction Data | Subsidy approvals · Grant disbursements · Title registrations · Complaint records | 4
Technology | 13. Technology Internal | Departmental data centre / SITA hosting · Provincial servers · End-user workstations | 3
| 14. Technology Integration | Batch file exchange (SFTP) · Point-to-point database links · Manual re-keying between systems | 3
| 15. Technology External | Deeds Office (DALRRD) · Home Affairs (DHA) · Municipalities · National Housing Finance Corporation | 4

## 2 · Assessment (P2)
PHASE 2 OUTPUT · MATURITY ASSESSMENT
Phase 2 — Maturity Assessment
Each element scored 0–5 (worst-dimension-wins), classified into a zone, with the spider chart and a chain analysis.
# | Element | Layer | Items | Score (0–5) | Target | Weight | Score × Weight | Zone | Element | Current | Target
1 | Outcome | Motivation | 7 | 2 | 3 | 1.5 | 3 | Intervene | Outcome | 2 | 3
2 | Client | Motivation | 10 | 1.9 | 3 | 1 | 1.9 | Intervene | Client | 1.9 | 3
3 | Value Proposition | Motivation | 5 | 2 | 3 | 1 | 2 | Intervene | Value Prop. | 2 | 3
4 | Capability | Strategy | 10 | 1.7 | 3 | 2 | 3.4 | Intervene | Capability | 1.7 | 3
5 | Location | Strategy | 11 | 1.64 | 3 | 0.5 | 0.82 | Intervene | Location | 1.64 | 3
6 | Product | Business | 9 | 2 | 3 | 1 | 2 | Intervene | Product | 2 | 3
7 | Service | Business | 20 | 1.55 | 3 | 1.5 | 2.325 | Intervene | Service | 1.55 | 3
8 | Process | Business | 22 | 1.45 | 3 | 1.5 | 2.175 | Intervene | Process | 1.45 | 3
9 | Application | IS Solution | 21 | 1.24 | 3 | 1.5 | 1.86 | Intervene | Application | 1.24 | 3
10 | Data Access | IS Solution | 24 | 0.5 | 3 | 2 | 1 | Intervene | Data Access | 0.5 | 3
11 | Master Data | IS Solution | 13 | 1 | 3 | 1.5 | 1.5 | Intervene | Master Data | 1 | 3
12 | Transaction Data | IS Solution | 16 | 1 | 3 | 1 | 1 | Intervene | Txn Data | 1 | 3
13 | Technology Internal | Technology | 9 | 0.78 | 3 | 1 | 0.78 | Intervene | Tech Int. | 0.78 | 3
14 | Technology Integration | Technology | 8 | 0.75 | 3 | 2 | 1.5 | Intervene | Tech Integ. | 0.75 | 3
15 | Technology External | Technology | 8 | 0.75 | 3 | 1 | 0.75 | Intervene | Tech Ext. | 0.75 | 3
| ENTERPRISE MATURITY INDEX (÷5 × 100) | [5 empty] | 26.01 | Intervene
Chain analysis — worked root cause (item score = MIN(ladder, gates, entity cap))
| Catalogue item |  | Ladder | Worst gate | Entity cap | Score | Binding dimension | Zone
| Data Access — beneficiary data exchange |  | 1.5 | 1.3 unencrypted/unlogged | 1 (one integration engineer) | 0.5 | 10.G1 + skills cap | Intervene
| Client — digitally excluded applicants |  | 0 | 0 | — | 0 | 2.L no digital channel | Intervene
| Outcome — informal settlements upgraded |  | 3 | 3 | 5 | 3 | 1.L managed | Improve

## 3 · Roadmap (P3)
PHASE 3 OUTPUT · PRIORITISATION & ROADMAP
Phase 3 — Prioritisation & Roadmap
Focus areas ranked by weighted gap = (target − current) × weight, then sequenced into three transition horizons.
Rank | Element | Layer | Current | Target | Weight | Weighted gap
1 | Data Access | IS Solution | 0.5 | 3 | 2 | 5
2 | Technology Integration | Technology | 0.75 | 3 | 2 | 4.5
3 | Master Data | IS Solution | 1 | 3 | 1.5 | 3
4 | Application | IS Solution | 1.24 | 3 | 1.5 | 2.64
5 | Capability | Strategy | 1.7 | 3 | 2 | 2.6
6 | Process | Business | 1.45 | 3 | 1.5 | 2.325
7 | Technology External | Technology | 0.75 | 3 | 1 | 2.25
8 | Technology Internal | Technology | 0.78 | 3 | 1 | 2.22
9 | Service | Business | 1.55 | 3 | 1.5 | 2.175
10 | Transaction Data | IS Solution | 1 | 3 | 1 | 2
11 | Outcome | Motivation | 2 | 3 | 1.5 | 1.5
12 | Client | Motivation | 1.9 | 3 | 1 | 1.1
13 | Value Proposition | Motivation | 2 | 3 | 1 | 1
14 | Product | Business | 2 | 3 | 1 | 1
15 | Location | Strategy | 1.64 | 3 | 0.5 | 0.68
Transition roadmap — three horizons
Horizon | Theme | When | Transition-architecture moves
H1 | Stabilise & enable | 0–12 months | Stand up change-and-delivery capability (clears the hard gate) · appoint a data steward and start the beneficiary golden record · replace hand-keying / flash-drives with a secured, logged file exchange (POPIA) · pilot one governed API for beneficiary look-up
H2 | Integrate | 12–24 months | MIOS-conformant integration layer / API gateway (PSR Reg 97) · departmental apps migrated to transversal governed platforms · beneficiary golden record consumed via API by provinces & metros · online subsidy application with status tracking
H3 | Transform to DPI | 24–36 months | Federated national interoperability (X-Road / DPI) for tenure & title · end-to-end citizen services pre-filled from national DPI · real-time verification of title deeds and subsidy eligibility
HARD GATE: the enabling-environment assessment finds no standing change-and-delivery capability. No ambitious architecture change may be scheduled until Horizon-1 builds it — see the EE · Readiness tab.

## 4 · Remedial (P4)
PHASE 4 OUTPUT · REMEDIAL ACTION PORTFOLIO
Phase 4 — Remedial Action Portfolio
The roadmap's transition architectures tracked as projects — stage, RAG status and progress.
Project | Addresses | Stage | RAG | Progress %
Change & Delivery Capability (PMO) | Hard gate | In delivery | Amber | 55%
Beneficiary Golden Record & stewardship | Master Data | In delivery | Green | 40%
Secure Data Exchange (retire re-keying) | Data Access | In delivery | Amber | 35%
MIOS-conformant Integration Layer | Tech Integration | Design | Red | 15%
Subsidy Application self-service | Service | Design | Amber | 20%
Application modernisation (→ transversal) | Application | Initiation | Green | 10%
Sequencing discipline: the PMO (hard gate) is most advanced; the integration layer is deliberately held at Red — it is blocked until delivery capability and the golden record mature. Every project traces to a Phase-3 focus area.

## 5 · Governance (P5)
PHASE 5 OUTPUT · GOVERNANCE & REPORTING
Phase 5 — Governance & Reporting
ARB submission register, principle-adherence scorecard and transformation impact — feeding the next cycle.
Architecture Review Board — submission register
Initiative | ARB decision |  | Standards alignment
Change & Delivery Capability (PMO) | Approved |  | Full
Beneficiary Golden Record | Approved |  | Full
Secure Data Exchange | Approved with conditions |  | Partial
Integration Layer (MIOS) | Under review |  | Pending
Subsidy self-service | Referred back |  | Gaps
Principle adherence
GWEA / DPI principle |  | Adherence %
Interoperability by default (MIOS) |  | 45%
Data as a shared asset (no silos) |  | 40%
Digital & self-service first |  | 30%
Security & privacy by design (POPIA) |  | 55%
Reuse before build |  | 50%
Impact of the transformation
Outcome measure |  | Baseline | Current
Subsidy applications lodged digitally |  | 0% | 22%
Beneficiary records with a golden record |  | 0% | 41%
Title-deed status verifiable in real time |  | No | Pilot
Enterprise maturity index |  | 26 | 31

## EE · Catalogue
ENABLING ENVIRONMENT · CATALOGUE
Enabling Environment — Catalogue
The Phase-1-style register of the enabling environment: what exists per readiness dimension, grouped into five clusters.
Grouping | Element / dimension | Enabling-environment items catalogued (illustrative) | Count
Mandate & Money | 1. Policy & regulatory reform | Housing Act 107 of 1997 · Prevention of Illegal Eviction (PIE) Act · PSR delegations & CGICTPF adoption · MIOS conformance mandate (PSR Reg 97) · Provincial housing legislation | 5
| 5. Funding & financial sustainability | Human Settlements Development Grant (HSDG) line · Urban Settlements Development Grant (USDG) line · Departmental ICT budget line · MTEF three-year allocation · APP budget programme structure | 5
| 6. Procurement & supply-chain agility | SITA mandated procurement channel · Departmental SCM policy · Transversal term contracts · Tender / bid register · Innovation-procurement route (not yet in place) | 5
Leadership | 4. Executive sponsorship & political will | Director-General digital mandate · ICT governance charter · GITO / DG steering forum · Standing transformation steering committee | 4
People & Culture | 2. Workforce & skills | IT / EA organisational structure · Competency framework & job profiles · Vacancy & skills-gap register · NSG / CSIR training plan · Contractor / SLA panel | 5
| 10. Change appetite & culture | Organisational change-management approach · Batho Pele culture programme · Adoption / uptake metrics | 3
| 11. Change & delivery capability ◄ HARD GATE | Programme / project office (PMO) charter — absent · Delivery method / SOPs · Project register · Key-person dependency log | 4
Data & Trust | 7. Data stewardship & sharing culture | Data governance policy · Named data-steward roles · Data-sharing agreements (Home Affairs, Deeds Office) · POPIA processing register | 4
| 8. Security, privacy & trust posture | Information security policy · POPIA compliance programme · ISO/IEC 27001 control set · Security incident register | 4
Citizen & Ecosystem | 3. Citizen digital empowerment | Multi-channel access plan · Digital-inclusion measures · Physical service / housing access points · PEPUDA compliance measures | 4
| 9. Partnership & ecosystem | NHFC & HDA partnership agreements · Municipal delivery agreements · Civil-society / community engagement · PPP instruments | 4

## EE · Readiness
ENABLING ENVIRONMENT · ASSESSMENT
Enabling Environment — Readiness Assessment
The catalogued dimensions scored 0–4 across five clusters, with the spider chart and the hard-gate verdict that governs the roadmap.
# | Dimension | Cluster | Rating (0–4) | Index (÷4×100) | Weight | Idx × Wt | Zone | Dimension | Current | Target
1 | Policy & regulatory reform | Mandate & Money | 2 | 50 | 1 | 50 | Improve | Policy & reform | 2 | 3
2 | Workforce & skills | People & Culture | 2 | 50 | 1.5 | 75 | Improve | Workforce | 2 | 3
3 | Citizen digital empowerment | Citizen & Ecosystem | 2 | 50 | 1 | 50 | Improve | Citizen empower. | 2 | 3
4 | Executive sponsorship & political will | Leadership | 3 | 75 | 1.5 | 112.5 | Sustain | Exec sponsor | 3 | 3
5 | Funding & financial sustainability | Mandate & Money | 2 | 50 | 1.5 | 75 | Improve | Funding | 2 | 3
6 | Procurement & supply-chain agility | Mandate & Money | 1 | 25 | 1.5 | 37.5 | Intervene | Procurement | 1 | 3
7 | Data stewardship & sharing culture | Data & Trust | 2 | 50 | 1 | 50 | Improve | Data steward | 2 | 3
8 | Security, privacy & trust posture | Data & Trust | 2 | 50 | 1.5 | 75 | Improve | Security | 2 | 3
9 | Partnership & ecosystem | Citizen & Ecosystem | 2 | 50 | 1 | 50 | Improve | Partnership | 2 | 3
10 | Change appetite & culture | People & Culture | 2 | 50 | 1 | 50 | Improve | Change culture | 2 | 3
11 | Change & delivery capability ◄ HARD GATE | People & Culture | 1 | 25 | 2 | 50 | Intervene | Delivery (GATE) | 1 | 3
| ENABLING-ENVIRONMENT READINESS INDEX (ERI) |  |  |  |  | 46.5517 | Intervene
Readiness by cluster (worst-dimension-wins sets the cluster zone)
| Cluster |  | Dimensions | Mean index | Worst dim |  | Zone
| Mandate & Money |  | 1, 5, 6 | 41.7 | Procurement (1) |  | Intervene
| Leadership |  | 4 | 75 | — |  | Sustain
| People & Culture |  | 2, 10, 11 | 41.7 | Delivery cap. (1) |  | Intervene
| Data & Trust |  | 7, 8 | 50 | — |  | Improve
| Citizen & Ecosystem |  | 3, 9 | 50 | — |  | Improve
HARD GATE — Dimension 11: NOT CLEARED. No standing change-and-delivery capability. Where the hard gate is not cleared, no ambitious architecture change may be scheduled until it is built.